## Slide 1: Action Plan: The Daily Cup Café
Pulse Marketing
Objective: In one month, reach 40K+ people, gain 500 followers, get 100+ messages and 10 more customers a day
Week | Task & Description | Responsible | Resources Needed | Monitor & Assess Progress | Review & Adjust
1 | Kick-off Meeting: Meet the owner, agree on the 4 goals and get page access. | Rahma Khaled Slides 1–3 | Meeting with the owner | Goals approved by the owner | Adjust goals if the owner asks
1 | Market Research: Study competitors and learn who the café's customers are. | Rahma Khaled Slides 1–3 | Google, competitors' pages, sales data | Research report ready by day 7 | Add a short survey in the café
1 | Page Audit: Check the café's Facebook and Instagram pages and list what to fix. | Abader Zarif Slides 11–13 | Page access, Meta Business Suite | Audit report ready by end of week 1 | Fix the biggest problems first
1–2 | Content Plan: Create a 30-day plan for posts, reels and stories. | Aya Reda Slides 4–6 | Google Sheets, café menu | Plan reviewed with the owner | Change topics based on feedback
2 | Photo Shoot: Take photos and videos of the menu, drinks and café. | Abader Zarif Slides 11–13 | Camera or phone, café visit | Check photo quality the same day | Reshoot weak photos
2–4 | Posts and Reels: Design 12 posts and 8 reels every month. | Aya Reda Slides 4–6 | Canva, CapCut, 3,000 EGP | Weekly check of likes and shares | Copy the style of the best posts
2–4 | Paid Ads: Run Facebook and Instagram ads for people near the café. | Mahmoud Ibrahim Slides 7–10 | Meta Ads Manager, 4,000 EGP | Daily check of reach and cost | Move money to the best ad
3–4 | Posting and Offers: Publish content, reply to messages and launch 2 offers. | Aya Reda Slides 4–6 | Meta Business Suite, 5,000 EGP | Weekly count of messages and offer sales | More reels, stronger offers
1–4 | Weekly Report: Track the 4 goals and send the owner a report every Sunday. | Mahmoud Ibrahim Slides 7–10 | Google Sheets, sales data, 1,000 EGP | Report every Sunday, with ROI | Fix weak numbers the next week
4 | Month-One Review: Review results with the owner and plan month two. | Abader Zarif Slides 11–13 | All reports, meeting with the owner | Compare results with the 4 goals | Recommendations for month two
Notes: This is our action plan for The Daily Cup, in the same format as the template. Objective: in one month, reach 40,000 people, gain 500 followers, get 100 messages and 10 more customers a day. Each row is one task, in order by week. For every task we show who is responsible, what we need, how we check progress, and what we change if it doesn't work. Each person owns the tasks for the slides they present: Rahma (slides 1 to 3), Aya (slides 4 to 6), Mahmoud (slides 7 to 10) and Abader (slides 11 to 13).